## Arkusz1
|  |  | AT THE BEGINNING OF THE DAY |  |  | ACTUAL WORKING HOURS
Sprint Start Date | 2020-04-17 | Day of the Sprint | Predicted Working Hours | Actual Working Hours | Day | Developer 1 | Developer 2 | Developer 3
Sprint End Date | 2020-04-24 | 1 | 40 | 40 | 1 | 2 | 2 | 3
Working Days | 5 | 2 | 34 | 34 | 2 | 3 | 3 | 4
Work Hours Per Day | 8 | 3 | 25 | 27 | 3 | 1 | 1 | 1
Total Available Hours | 40 | 4 | 16 | 16 | 4 | 4 | 2 | 1
Average Daily Available Hours | 8 | 5 | 10 | 11 | 5 | 1 | 1 | 1
Number of People Working | 3 | 6 | 6 | 7 | 6 | 1 | 1 | 2
|  | 7 | 4 | 5 | 7 | 1 | 2 | 1
[5 empty] | Total | 13 | 12 | 13